## MS01
|  | Milestone - 01 | Result
|  | Get information about the feasibility of the project | [2018-05-04] Project is feasible, milestone closed
#ISSUE | State | PROBLEMS | RESULT | Comment
1 | SOLVED | Determine the LED's Forward Current | IF: 60mA (20mA/diode) | 3 diode is in one 5050 smd led chip
2 | SOLVED | Determine the LED's Forward Voltage | UF: 3V-3.4V
3 | SOLVED | Compute the resistor value | R = UF/IF: 50ohm - 56ohm | for UF source voltage there is no need for resistor
5 | SOLVED | Chose a battery type considering the Voltage and Lifetime of the construction. | Battery type: 2 AA Alkaline (serial) can produce 3V and 2000mAh size: 50x15mm (50x30mm) OR Battery type: 2 D Alkaline (serial) can produce 3V and 15000mAh size: 62x33mm (62x66mm) | for 2 led can ensure 2000/120= 16 hours OR 15000/120= 125 hours
6 | SOLVED | Build a test curcit with defined values | Result: works with rgb led, white is not tested yet [2018-05-04] white also tested, works fine | projection is visible, and quite big: more than 15 cm tall
7 | SOLVED | Choose boxing | Plastic container can be used with silver decor tape
8 | SOLVED | Make it switchable | Slide switch can be used

## MS02
|  | Milestone - 02 | Result
Test and create a prototype of product
#ISSUE | State | PROBLEMS | RESULT | Comment | Init date
1 | OPEN | Fit parts to the boxes |  | Parts fits to the box, not fixed yet | 2018-05-04
2 | OPEN | Determine the positions of the leds |  | Lighting angle shall be 45° to horizon | 2018-05-04
3 | OPEN | Find a way to hang it to wall |  |  | 2018-05-04

## MS03
|  | Milestone - 03 | Result
Make the product remote controllable.
#ISSUE | State | PROBLEMS | RESULT | Comment | Init date
1 | OPEN | Create a Test circuit for infra reciever |  |  | 2018-05-04

## help
OPEN
WORK
SOLVED